## Schedule
Route Optimization - Intracity | [47 empty] | [42]
The Baker's Dozen
| #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
TASK DESCRIPTION | May | [11 empty] | June | [11 empty] | July | [11 empty] | August
| Week 1 |  |  | Week 2 |  |  | Week 3 |  |  | Week 4 |  |  | Week 1 |  |  | Week 2 |  |  | Week 3 |  |  | Week 4 |  |  | Week 1 |  |  | Week 2 |  |  | Week 3 |  |  | Week 4 |  |  | Week 1 |  |  | Week 2 |  |  | Week 3 |  |  | Week 4
Phase 1: Understanding the concept of Route Optimization
Task 1- Clearly articulate the objectives
Task 2- Finding the constraints
Task 3 - Identify the specific goals
Phase 1 Milestone A- 1) Minimizing travel time 2) Maximizing resource utilization 3) Minimize Cost 4) Automatically Find the optimize routes if new service location is added | [8 empty] | ` | ` | [50 empty] | Slot Time Constraints ->> Create Master data
Phase 2: Data Collection
Task 1-Information about the locations to be visited
Task 2-Geographical coordinates
Task 3-service time windows
Task 4-vehicle capacity constraints
Phase 3: Data Processing and Transformation
Task 1- Includes Cleaning data for Delhi Location
Phase 4: Selecting Optimization Technique
A) Selected Heuristic Algorithm
Task 1- Calculate Distance Matrix for Sample Data-Set
Task 2- Understanding Excel Solver and Implementing the technique
Phase 4 Milestone A- The technique proved ineffectual for our Dataset
B) Selected Travelling Salesman Algorithms
Phase 4 Milestone B- Provided us with the optimal route for 15 Location
Phase 5: Finalization of Model
Phase 6: Implementation of Optimized Algorithm
Phase 7: Evaluate and Fine Tune the Model
Phase 8: Implement and Monitor at Intracity Level

## Sheet1
Cost:
FC- optimized KMs( least distance value)->> less Deisel cost->> FC reduced
VC - reduced Kms
Resource Utilization : Trip wise Carton Size? On daily basis how much we shift ->> Tempo utlizied